## Consolidated Playbooks
Rank | Priority | Playbook Name | What it Does | # Times Ran | Assigned To | Status | Status Comments | Automation Project Name | Teams Folder | Complexity | Notes / Gotchas | Ansible Job Name | Authentication Type | Ansible Inventory | Target OS / Platform | Orchestrator Connection Type | External File Dependencies | All Files Used | AAP Template 1 | AAP Template 2 | AAP Template 3 | AAP Template 4 | AAP Template 5 | AAP Template 6 | AAP Template 7 | AAP Template 8 | AAP Template 9 | AAP Template 10
1 | Critical | file-move_with-UNCPath_AD-Group.yml | Queries AD for computer objects in a security group, builds a dynamic inventory, then moves files older than N days from UNC source paths to a target share using an inline PowerShell function. | 262 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | Dynamically builds inventory from AD security group — Orchestrator will need a different approach. Consider using PowerShell to query AD directly in a scriptable task, then iterate over results. Inline PowerShell function handles the file move logic. | 1P_DPT_CONNECT__EW_file-move_with-UNCPath_AD-Group 1P_DPT_CONNECT__BMIC_OW_file-move_with-UNCPath_AD-Group 1P_ConvergedL3-move_with-UNCPath_AD-Group 1P_EMAT_file-move_with-UNCPath_AD-Group 1P_ConvergedL3_file-move_with-UNCPath_AD-Group-connect | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; AD group DN and parameters supplied at runtime | Playbook: psscript/file-move_with-UNCPath_AD-Group.yml | 1P_DPT_CONNECT__EW_file-move_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-DPT-ESOC_West-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0' | 1P_DPT_CONNECT__BMIC_OW_file-move_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-DPT-BIMC_OW-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0' | 1P_ConvergedL3-move_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-Converged-All-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0' | 1P_EMAT_file-move_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-Monitoring-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0' | 1P_ConvergedL3_file-move_with-UNCPath_AD-Group-connect extra_vars: group_dn: CN=CVS-Converged-All-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0'
1 | High | move-win-archived-logs.yml | Runs a PowerShell script to move archived Windows logs to a file share target. | 66 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | External PS script copies archived Windows logs to a file share. Straightforward once PS script logic is understood. Only 2 templates. | 1P_SEC_WinServer_Archives.Files.Move 1P_DPT_EW_WinServer_Archives.Files.Move | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/move-win-archived-logs.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_WinServer_Archives.Files.Move extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: move-archived-logs var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-Security-Servers var_FileShareTarget: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows | 1P_DPT_EW_WinServer_Archives.Files.Move extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: move-archived-logs var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-DPT-EW_Servers var_FileShareTarget: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows
1 | High | file-move_with-UNCPath_AD-Group-TEST.yml | Test variant of UNC file move. Adds explicit AD credential handling (PSCredential) for environments requiring authenticated AD queries. Same move logic as the production version. | 56 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | Test variant with explicit PSCredential handling for AD queries. Nearly identical to main file-move playbook. Can likely consolidate into single Orchestrator workflow with a credentials toggle. | 1P_DPT_Action-BIMC-OW_Archives.Files.Move_WinServer | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; AD group DN and parameters supplied at runtime | Playbook: psscript/file-move_with-UNCPath_AD-Group-TEST.yml | 1P_DPT_Action-BIMC-OW_Archives.Files.Move_WinServer extra_vars: DomainName: connect.sbu group_dn: CVS-DPT-BIMC_OW_Servers source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0'
1 | High | file-move_with-UNCPath_AD-Group-TEST(1).yml | Second test variant of UNC file move. Uses -Server parameter for cross-domain AD queries (specifies DomainName). Same core move logic. | 38 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | Second test variant using -Server parameter for cross-domain AD queries. Can likely merge with main file-move workflow using a "domain server" input parameter. | 1P_ConvergedL3_file-move_with-UNCPath_AD-Group | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; AD group DN and parameters supplied at runtime | Playbook: psscript/file-move_with-UNCPath_AD-Group-TEST(1).yml | 1P_ConvergedL3_file-move_with-UNCPath_AD-Group extra_vars: DomainName: washdc.state.sbu group_dn: CVS-ConvergedL3-Servers source_path: C$\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0'
1 | High | file-move_with-LocalPath_Inventory.yml | Moves archived log files from a local source path to a share target on Windows hosts from the static inventory (no AD lookup). Uses an inline PowerShell Move-files function. | 38 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | Simpler variant using static inventory instead of AD lookup. Inline PowerShell Move-files function. Good candidate for consolidation with UNC path variant. | 1P_EMAT_file-move_with-LocalPath_Inventory | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; source_path, target_path, file_filter, days_old supplied at runtime | Playbook: psscript/file-move_with-LocalPath_Inventory.yml | 1P_EMAT_file-move_with-LocalPath_Inventory extra_vars: source_path: C:\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '-1'
1 | Low | file-move_with-LocalPath_AD-Group.yml | Queries AD for computer objects in a security group, builds a dynamic inventory, then moves files from local paths on each server to a target share using a two-play design (inventory build, then execute on dynamic group). | 0 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | Two-play design: first queries AD for dynamic inventory, second executes on discovered hosts. Same AD-driven inventory challenge as other file-move variants. | 1P_EMAT_file-move_with-LocalPath_AD-Group | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; AD group DN and parameters supplied at runtime | Playbook: psscript/file-move_with-LocalPath_AD-Group.yml | 1P_EMAT_file-move_with-LocalPath_AD-Group extra_vars: group_dn: CN=CVS-Monitoring-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C:\Windows\System32\winevt\Logs target_path: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows file_filter: Archive-*.evtx days_old: '0'
52 | Low | remove-OldFiles-UNCPath.yml | Runs a PowerShell script to remove old files from a UNC share path, with WhatIf dry-run toggle. | 0 | Jeremy Forguson | Completed |  | Move Archived Event Logs | psscript | M | External PS script removes old files from UNC paths. Supports WhatIf (dry-run) — preserve this as a boolean input in Orchestrator. | 1P_EMAT_Remove-OldFiles-UNCPath | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/ps_scripts/cvs_functions.ps1 | Playbook: psscript/remove-OldFiles-UNCPath.yml File: psscript/files/ps_scripts/cvs_functions.ps1 | 1P_EMAT_Remove-OldFiles-UNCPath extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Delete-OldFiles-UNC-Share var_UNC_SharePath: \\esoco26cdt3-100.washdc.state.sbu\mdcarchivelog$\Windows var_OlderThanDays: 370 var_WhatIf: 'no'
2 | Critical | servers_reboot.yml | Runs a PowerShell script to reboot Windows servers from an AD group with configurable delay between reboots and email reporting. | 200 |  |  |  | Reboot Servers | psscript | M | Copies and executes an external PowerShell script via WinRM. PS script handles AD group enumeration, reboot sequencing with configurable delays, and email reporting. 10 AAP templates = many environment-specific variable sets. | 1P_EMAT_Server_Reboot_GP02 1P_DPT_Action-Auto_Reboot_Mgmt_Servers 1P_ConvergedL3_Server_Reboot_GP02-connect 1P_ConvergedL3_Server_Reboot_GP02 1P_SEC_Server_Reboot 1P_ConvergedL3_Server_Reboot_GP 1P_EMAT_Server_Reboot_GP01 P_ConvergedL3_Server_Reboot_GP01-connect 1P_DPT_Action-MANUAL_Server_Reboot_CSDR-PXYs 1P_DPT_MANUAL_CONNECT_Server_Reboot_PXY | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/servers_reboot.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_EMAT_Server_Reboot_GP02 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: connect.sbu var_OUPath: OU=Groups,OU=State Dept,DC=connect,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Monitoring-Reboot-Servers-GP02 var_HeaderNotesSubstr: CVS-Monitoring-Reboot-Servers-GP02 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 10 | 1P_DPT_Action-Auto_Reboot_Mgmt_Servers extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DT-CVS-Data-Protection-Team-FL@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: DPT Servers Reboot status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-DPT-MgmtServers var_HeaderNotesSubstr: CVS-DPT-MgmtServers var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_ConvergedL3_Server_Reboot_GP02-connect extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: connect.sbu var_OUPath: OU=Groups,OU=State Dept,DC=connect,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Converged-Reboot-Servers-GP02 var_HeaderNotesSubstr: CVS-Converged-Reboot-Servers-GP02 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_ConvergedL3_Server_Reboot_GP02 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-ConvergedL3-Reboot-Servers-GP02 var_HeaderNotesSubstr: CVS-ConvergedL3-Reboot-Servers-GP02 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_SEC_Server_Reboot extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'no' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DTHISecurityFL@state.gov,amsaem@state.gov,esocsecurityteam@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Security-Reboot-Servers var_HeaderNotesSubstr: CVS-Security-Reboot-Servers var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 10 | 1P_ConvergedL3_Server_Reboot_GP extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-ConvergedL3-Reboot-Servers-GP01 var_HeaderNotesSubstr: CVS-ConvergedL3-Reboot-Servers-GP01 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_EMAT_Server_Reboot_GP01 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: connect.sbu var_OUPath: OU=Groups,OU=State Dept,DC=connect,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Monitoring-Reboot-Servers-GP01 var_HeaderNotesSubstr: CVS-Monitoring-Reboot-Servers-GP01 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 10 | P_ConvergedL3_Server_Reboot_GP01-connect extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: connect.sbu var_OUPath: OU=Groups,OU=State Dept,DC=connect,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Converged-Reboot-Servers-GP01 var_HeaderNotesSubstr: CVS-Converged-Reboot-Servers-GP01 var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_DPT_Action-MANUAL_Server_Reboot_CSDR-PXYs extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-DPT-Manual_Reboot_Servers var_HeaderNotesSubstr: CVS-DPT-Manual_Reboot_Servers var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5 | 1P_DPT_MANUAL_CONNECT_Server_Reboot_PXY extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Invoke-ServerReboot var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: NguyenTD4@state.gov var_MailCcString: NguyenTD4@state.gov var_MailSubjectstring: 'Ansible-Report: ESOC Monitoring Servers Reboot status' var_DomainName: CONNECT.sbu var_OUPath: CN=CVS-DPT-Reboot_Auto,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_cleanup_temporary_folder: true var_ADGroupMember: CVS-DPT-Reboot_Auto var_HeaderNotesSubstr: CVS-DPT-Reboot_Auto var_RebootIt: simpleMode var_RebootIt_DelayBetweenServer: 5
3 | Critical | vm_remove_snapshot.yml | Removes VM snapshots by applying a vm_snapshot role with vCenter credentials. | 190 | Jeremy Forguson | Complete |  |  | vmops | S | Uses a role wrapping community.vmware.vmware_guest_snapshot. Orchestrator has native snapshot actions in the vCenter plugin — should be one of the simplest conversions. 6 templates differ only by vCenter hostname. | 1V_ConvergedL3_esoco26vcs01_Snapshot_removal _SPLUNK 1V_ConvergedL3_esocoewvcs_Snapshot_removal 1V_ConvergedL3_esocoewvcs01_Snapshot_removal 1V_ConvergedL3_esocoewvcs02_Snapshot_removal 1V_ConvergedL3_esoco26vcs01_Snapshot_removal 1V_ConvergedL3_esoco26vcs02_Snapshot_removal | vCenter service account, domain service account | aap controller | vCenter/ESXi | vCenter Plugin | Yes — Role: roles/vm_snapshot/ | Playbook: vmops/vm_remove_snapshot.yml Role: vmops/roles/vm_snapshot/ | 1V_ConvergedL3_esoco26vcs01_Snapshot_removal _SPLUNK extra_vars: vcenter_hostname: esoco26vcs01.washdc.state.sbu datacenter_name: - VXRL-Cluster07-Splunk var_snapshotage: 2 snapshot_name_filter: '' | 1V_ConvergedL3_esocoewvcs_Snapshot_removal extra_vars: vcenter_hostname: esocoewvcs.washdc.state.sbu datacenter_name: - 02-CVS-VXrail-EW var_snapshotage: 3 snapshot_name_filter: '' | 1V_ConvergedL3_esocoewvcs01_Snapshot_removal extra_vars: vcenter_hostname: esocoewvcs01.washdc.state.sbu datacenter_name: - 00-NSXT-VXrail-EW var_snapshotage: 3 snapshot_name_filter: '' | 1V_ConvergedL3_esocoewvcs02_Snapshot_removal extra_vars: vcenter_hostname: esocoewvcs02.washdc.state.sbu datacenter_name: - 01-ESOC-VXRAIL var_snapshotage: 3 snapshot_name_filter: '' | 1V_ConvergedL3_esoco26vcs01_Snapshot_removal extra_vars: vcenter_hostname: esoco26vcs01.washdc.state.sbu datacenter_name: - 01-CVS-VXrail-HST - 01-CVS-VXrail-MDC3 var_snapshotage: 3 snapshot_name_filter: '' | 1V_ConvergedL3_esoco26vcs02_Snapshot_removal extra_vars: vcenter_hostname: esoco26vcs02.washdc.state.sbu datacenter_name: - 00-NSXT-VXrail-BIMC var_snapshotage: 10 snapshot_name_filter: ''
2 | Critical | servers_reboot_report-ByCN.yml | Same as the reboot report but filters by Security Group CN instead of ADGroupMember. | 180 |  |  |  | Pending Reboot Report | psscript | M | Similar to servers_reboot but filters by Security Group CN. Same external PS script dependency. Email reporting included. | 1P_DPT_Report-CONNECT_EW_ServerPendingRebootStatus 1P_DPT_Report-CONNECT_BIMC_OW_ServerPendingRebootStatus 1P_EMAT_ServerPendingRebootStatus 1P_ConvergedL3_ServerPendingRebootStatus-CONNECT 1P_ConvergedL3_ServerPendingRebootStatus | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/servers_reboot_report-ByCN.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_DPT_Report-CONNECT_EW_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerRebootReportStatus-ByCN var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DT-CVS-Data-Protection-Team-FL@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS DPT CONNECT EW Server Reboot status' var_cleanup_temporary_folder: true var_HeaderNotesSubstr: CVS-DPT-ESOC_West-Servers var_SecurityGroup_CN: CN=CVS-DPT-ESOC_West-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_DomainName: connect.sbu | 1P_DPT_Report-CONNECT_BIMC_OW_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerRebootReportStatus-ByCN var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DT-CVS-Data-Protection-Team-FL@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS DPT CONNECT BIMC and HST-OW Server Reboot status' var_cleanup_temporary_folder: true var_HeaderNotesSubstr: CVS-DPT-BIMC_OW-Servers var_SecurityGroup_CN: CN=CVS-DPT-BIMC_OW-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_DomainName: connect.sbu | 1P_EMAT_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerRebootReportStatus-ByCN var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: Nguyentd4@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Monitoring Servers Reboot status' var_cleanup_temporary_folder: true var_HeaderNotesSubstr: CVS-Monitoring-Servers var_SecurityGroup_CN: CN=CVS-Monitoring-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_DomainName: connect.sbu | 1P_ConvergedL3_ServerPendingRebootStatus-CONNECT extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerRebootReportStatus-ByCN var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DTCVSOn-PremEngineering@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Converged Servers Reboot status (CONNECT)' var_cleanup_temporary_folder: true var_HeaderNotesSubstr: CVS-Converged-All-Servers var_SecurityGroup_CN: CN=CVS-Converged-All-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_DomainName: connect.sbu | 1P_ConvergedL3_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerRebootReportStatus-ByCN var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DTCVSOn-PremEngineering@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Converged Servers Reboot status' var_cleanup_temporary_folder: true var_HeaderNotesSubstr: CVS-ConvergedL3-Servers var_SecurityGroup_CN: >- CN=CVS-ConvergedL3-Servers,OU=Servers GP,OU=Security Groups,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_DomainName: washdc.state.sbu
5 | High | servers_diskclean.yml | Runs a PowerShell disk cleanup script on Windows servers with folder, filter, and age parameters. | 77 |  |  |  |  | psscript | M | External PS script with many parameters (target folder, included folders, force enable, days, filter). 8 templates. Two templates delete user profiles (different PS function) — may warrant a separate workflow. | 1P_SEC_WinServer_DiskClean 1P_DPT_WinServer_DiskClean 1P_DPT_CONNECT_WinServer_DiskClean 1P_EMAT_WinServer_DiskClean 1P_ConvergedL3_WinServer_DiskClean 1P_EMT_WinServer_DiskClean 1P_ConvergedL3_Delete_User_Profile_MDC 1P_ConvergedL3_Delete_User_Profile_EW | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/servers_diskclean.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-Security-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_DPT_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_DomainName: connect.sbu var_ADGroupMember: CVS-DPT-AllServers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_DPT_CONNECT_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_DomainName: CONNECT.sbu var_ADGroupMember: CVS-DPT-All-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_EMAT_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_DomainName: connect.sbu var_ADGroupMember: CVS-Monitoring-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_ConvergedL3_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-ConvergedL3-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_EMT_WinServer_DiskClean extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_ADGroupMember: CVS-Monitoring-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'no' var_NumberOfDays: '-1' var_FilterOn: '*.*' var_FolderTarget: - c:\Windows\ccmcache | 1P_ConvergedL3_Delete_User_Profile_MDC extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_ADGroupMember: CVS-ConvergedL3-MDC-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'yes' var_NumberOfDays: '0' var_FilterOn: '*.*' var_FolderTarget: - c:\users | 1P_ConvergedL3_Delete_User_Profile_EW extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: clean-ServerDisk var_ADGroupMember: CVS-ConvergedL3-EW-Servers var_FolderIncluded: 'yes' var_ForceEnable: 'yes' var_NumberOfDays: '0' var_FilterOn: '*.*' var_FolderTarget: - c:\users
8 | High | servers_pending_reboot_report.yml | Runs a PowerShell script that queries AD group members for pending reboot status and sends an email report. | 42 |  |  |  |  | psscript | M | External PS script queries AD group members for pending reboot status and generates email report. Same WinRM + PS script pattern. | 1P_SEC_ServerPendingRebootStatus 1P_DPT_Report-EW_ServerPendingRebootStatus 1P_DPT_Report-BIMC_OW_ServerPendingRebootStatus | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/servers_pending_reboot_report.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerPendingRebootStatus var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: ' DTHISecurityFL@state.gov,amsaem@state.gov,esocsecurityteam@state.gov' var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Security Servers Reboot status' var_DomainName: washdc.state.sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-Security-Servers var_HeaderNotesSubstr: CVS-Security-Servers | 1P_DPT_Report-EW_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerPendingRebootStatus var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DT-CVS-Data-Protection-Team-FL@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Data Protecton ESOC West Servers Reboot status' var_DomainName: washdc.state.sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-DPT-EW_Servers var_HeaderNotesSubstr: CVS-DPT-EW_Servers | 1P_DPT_Report-BIMC_OW_ServerPendingRebootStatus extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServerPendingRebootStatus var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DT-CVS-Data-Protection-Team-FL@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Data Protecton BIMC and HST-OW Servers Reboot status' var_DomainName: washdc.state.sbu var_cleanup_temporary_folder: true var_ADGroupMember: CVS-DPT-BIMC_OW_Servers var_HeaderNotesSubstr: CVS-DPT-BIMC_OW_Servers
9 | High | admin_accounts_report-v2.yml | V2 of the admin accounts report. Writes a DomainOUs JSON file to the target before executing the PowerShell script, supporting multi-domain OU input. | 39 |  |  |  |  | psscript | M | V2 adds a pre-step writing a DomainOUs JSON file to the target before running the PS script. Orchestrator workflow needs JSON file generation as a separate scriptable task before the main report. | 1P_SEC_Admin_Accounts_Status-WASHDC-v2 1P_SEC_Admin_Accounts_Status-v2 1P_SEC_Admin_Accounts_Status-v2-TEST | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/admin_accounts_report-v2.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_Admin_Accounts_Status-WASHDC-v2 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: CVS OCUNUS (WASHDC) - Admin PKI Card Status' var_DomainName: washdc.state.sbu var_OUPath: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=washdc,DC=state,DC=sbu | 1P_SEC_Admin_Accounts_Status-v2 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions-v2.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: >- DTHISecurityFL@state.gov,DT-CVS-Data-Protection-Team-FL@state.gov,DTCVSOn-PremEngineering@state.gov,DTCVSVGEFL@state.gov var_MailCcString: >- amsaem@state.gov,esocsecurityteam@state.gov,DTCVSMonitoring@state.gov,DTHISecurityFL@state.gov var_MailSubjectstring: 'Ansible-Report: Admin PKI Card Status' var_DomainOUs: neasa.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=neasa,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=neasa,DC=state,DC=sbu eap.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=eap,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=eap,DC=state,DC=sbu washdc.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=washdc,DC=state,DC=sbu - OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu af.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=af,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=af,DC=state,DC=sbu eur.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=eur,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=eur,DC=state,DC=sbu wha.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=wha,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=wha,DC=state,DC=sbu appservices.state.sbu: - >- OU=Admin Accounts,OU=Data Offshoring,OU=Enterprise Services,DC=appservices,DC=state,DC=sbu | 1P_SEC_Admin_Accounts_Status-v2-TEST extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions-v2.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: Admin PKI Card Status' var_DomainOUs: neasa.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=neasa,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=neasa,DC=state,DC=sbu eap.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=eap,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=eap,DC=state,DC=sbu washdc.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=washdc,DC=state,DC=sbu - OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu af.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=af,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=af,DC=state,DC=sbu eur.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=eur,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=eur,DC=state,DC=sbu wha.state.sbu: - >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=wha,DC=state,DC=sbu - OU=Admin Accounts,OU=Data Offshoring,OU=GITM-U,DC=wha,DC=state,DC=sbu appservices.state.sbu: - >- OU=Admin Accounts,OU=Data Offshoring,OU=Enterprise Services,DC=appservices,DC=state,DC=sbu
12 | High | command.yml | Runs an arbitrary Cisco NX-OS command (passed via {{var_command}}) on targeted switches. Generic utility playbook. | 32 |  |  |  |  | networking | S | Runs a single arbitrary NX-OS command via SSH. Very simple — one scriptable task. 6 templates all pass different show commands. Good general-purpose "run NX-OS command" workflow. | 1N_NET_Nex9k_Command 1N_NET_Nex9k_Command_SNMP 1N_NET_Nex9k_Command_CDP 1N_NET_Nex9k_Command_Console 1N_NET_Nex9k_Command_STP 1N_NET_Nex9k_Command_MOTD | ssh | NEXUS-9X constructed, na, NEXUS-9x constructed | Cisco NX-OS | SSH Connection |  | Playbook: networking/command.yml | 1N_NET_Nex9k_Command extra_vars: var_command: show clock | 1N_NET_Nex9k_Command_SNMP extra_vars: var_command: show clock | 1N_NET_Nex9k_Command_CDP extra_vars: var_command: show clock | 1N_NET_Nex9k_Command_Console extra_vars: var_command: show clock | 1N_NET_Nex9k_Command_STP extra_vars: var_command: show clock | 1N_NET_Nex9k_Command_MOTD extra_vars: var_command: show clock
13 | High | service_accounts_report.yml | Runs a PowerShell script to report on service account expirations from a specified AD OU path, with email delivery. | 31 |  |  |  |  | psscript | M | External PS script reports on service account expirations from AD OU paths. Same WinRM + PS copy/execute pattern. Email delivery included. | 1P_SEC_Service_Account_Expiration_Report 1P_SEC_Service_Account_Expiration_Report-TEST 1P_SEC_Service_Account_Expiration_Report-OCUNUS | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/service_accounts_report.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_Service_Account_Expiration_Report extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServiceAccountExpiration var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: >- DTHISecurityFL@state.gov,DTCVSOn-PremEngineering@state.gov,DT-CVS-Data-Protection-Team-FL@state.gov,ESOCSecurityTeam@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Service Account Expiration Report' var_DomainName: washdc.state.sbu var_OUPath: OU=Service Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true | 1P_SEC_Service_Account_Expiration_Report-TEST extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServiceAccountExpiration var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Service Account Expiration Report' var_DomainName: connect.sbu var_OUPath: CN=CVS_Service_Accounts,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU var_cleanup_temporary_folder: true | 1P_SEC_Service_Account_Expiration_Report-OCUNUS extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get-ServiceAccountExpiration var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: CVS OCONUS (WASHDC) - Service Account Expiration Report' var_DomainName: washdc.state.sbu var_OUPath: >- OU=Service Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=washdc,DC=state,DC=sbu var_cleanup_temporary_folder: true
14 | Medium | get_datastores_75_100_used.yml | Runs a PowerShell script to report on VMware datastores at 75–100% utilization, with email reporting and vCenterList inputs. | 29 |  |  |  |  | psscript | M | PS script queries vCenter for datastore utilization via PowerCLI. Despite targeting vCenter data, runs via WinRM/PowerShell. Orchestrator alternative: use vCenter plugin datastore inventory directly. | 1P_ConvergedL3_Get_Datastores_75_100_Used | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/get_datastores_75_100_used.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_ConvergedL3_Get_Datastores_75_100_Used extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: Get_Datastores_75_100_Used var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DTCVSOn-PremEngineering@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: Datastore Report' var_cleanup_temporary_folder: true var_vCenterList: >- esocoewvcs01.washdc.state.sbu, esoco26vcs01.washdc.state.sbu, esoco26vcs02.washdc.state.sbu, esocoewvcs.washdc.state.sbu, esocoewvcs02.washdc.state.sbu
15 | Medium | nexus_upgrades/staging-with-scp.yml | Enhanced N9kv staging with pre-flight checks: validates variables, tests TCP/22, verifies bootflash space, performs SCP copy, verifies file size + SHA512, then restores timeout and disables SCP. | 19 |  |  |  |  | networking | L | Complex staging: validates variables, tests TCP/22, checks bootflash free space (10% buffer), SCP copy, verifies size + SHA512, restores VTY timeout. Multiple sequential SSH commands with error handling. 8 templates. | 1N_NET_EW_Nex9k_Staging-11 1N_NET_HST_TESTSwitch_Staging @ 08:50:20 1N_NET_HST_TESTSwitch_Staging 1N_NET_HST_Nex9k_Staging-11 1N_NET_HST_Nex9k_Staging-12 1N_NET_MDC_Nex9k_Staging-11 1N_NET_MDC_Nex9k_Staging-12 1N_NET_EW_Nex9k_Staging-10 | ssh | EW-Nex9k-key, HST-TESTswitch-Nex9k-key, HST-Nex9k-key, MDC-Nex9k-key, MDC-Nex9k | Cisco NX-OS | SSH Connection | Yes — External file: {{remote_file}} on {{remote_scp_server}} | Playbook: networking/nexus_upgrades/staging-with-scp.yml External: SCP file on remote server | 1N_NET_EW_Nex9k_Staging-11 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.68.6.78 cisco_vrf: management new_image: nxos64-cs.10.5.4.M.bin expected_file_size: 2891288576 sha_hash: >- 7967343da50fe31e7cbd0d660e8550994448e1fee401696c6f6b9fb0c9e079423a81e7266c7868061459a1c60320f3949ce1565635eed0d9b98cad050f7ff474 | 1N_NET_HST_TESTSwitch_Staging @ 08:50:20 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 1800 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.3.128.165 cisco_vrf: default new_image: nxos64-cs.10.5.5.M.bin expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_HST_TESTSwitch_Staging extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 1800 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.3.128.165 cisco_vrf: default new_image: nxos64-cs.10.5.5.M.bin expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_HST_Nex9k_Staging-11 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.3.128.165 cisco_vrf: management new_image: nxos64-cs.10.5.5.M.bin expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_HST_Nex9k_Staging-12 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.3.128.164 cisco_vrf: default new_image: nxos64-cs.10.5.5.M.bin expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_MDC_Nex9k_Staging-11 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 new_image: nxos64-cs.10.5.5.M.bin remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.20.33.96 cisco_vrf: management expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_MDC_Nex9k_Staging-12 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 new_image: nxos64-cs.10.5.5.M.bin remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.20.33.97 cisco_vrf: default expected_file_size: 2895731712 sha_hash: >- d05b8fb0df63d1b16974139dde84f6b6174ffed67e57d55ec4c352434dfd69d606ef4ee8c35109761d4caee3771b1ab4d99fa02e68ed896d1e13ba2252d85dca | 1N_NET_EW_Nex9k_Staging-10 extra_vars: _groups: n9kv exec_timeout_transfer: 60 scp_timeout_sec: 2400 remote_file: /var/cvs-scp/{{ new_image }} remote_scp_server: 10.68.6.77 cisco_vrf: management new_image: nxos64-cs.10.5.4.M.bin expected_file_size: 2891288576 sha_hash: >- 7967343da50fe31e7cbd0d660e8550994448e1fee401696c6f6b9fb0c9e079423a81e7266c7868061459a1c60320f3949ce1565635eed0d9b98cad050f7ff474
16 | Medium | account_password_update.yml | Resets an Active Directory account password using the microsoft.ad collection and AAP controller integration. Delegates to the 'account' role. | 18 |  |  |  |  | admins | L | Uses microsoft.ad collection and AAP controller API. Delegates to a role. Orchestrator needs REST endpoint for AAP controller calls (if retained) plus PowerShell/AD module calls for password reset. 3 templates for 3 service accounts. | 1A_PW-Change_svcCVSAnsWin 1A_PW-Change_svcCVSAnsVC 1A_PW-Change_svcCVSAnsAdmin | domain service account | WinRM_servers | Windows | PowerShell Host, REST Host | Yes — Role: roles/account/; Collections: microsoft.ad, ansible.controller | Playbook: admins/account_password_update.yml Role: admins/roles/account/ | 1A_PW-Change_svcCVSAnsWin extra_vars: var_sAMAccountName: svcCVSAnsWin var_LDAPUsername: svcCVSAnsWin@WASHDC.STATE.SBU var_domain_server: MSWASHDCDC02.washdc.state.sbu var_LDAPBaseDN: OU=Service Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_AAP_Credentials: svcCVSAnsWin var_AAP_VCenter_Host: '' var_AAP_organization: cvs var_Credential_type: - Machine - cvs-WinRM_Cred controller_host: https://cvsautomation.washdc.state.sbu var_debug: 123 | 1A_PW-Change_svcCVSAnsVC extra_vars: var_sAMAccountName: svcCVSAnsVC var_LDAPUsername: svcCVSAnsVC@WASHDC.STATE.SBU var_domain_server: MSWASHDCDC02.washdc.state.sbu var_LDAPBaseDN: OU=Service Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_AAP_Credentials: svcCVSAnsVC var_AAP_VCenter_Host: '' var_AAP_organization: cvs var_Credential_type: - Machine - cvs-CenterAdmin_Cred controller_host: https://cvsautomation.washdc.state.sbu var_debug: 123 | 1A_PW-Change_svcCVSAnsAdmin extra_vars: var_sAMAccountName: svcCVSAnsAdmin var_LDAPUsername: svcCVSAnsAdmin@WASHDC.STATE.SBU var_domain_server: MSWASHDCDC02.washdc.state.sbu var_LDAPBaseDN: OU=Service Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu var_AAP_Credentials: svcCVSAnsAdmin var_AAP_VCenter_Host: '' var_AAP_organization: cvs var_Credential_type: - Machine controller_host: https://cvsautomation.washdc.state.sbu var_debug: 123
17 | Medium | file-deletion_with-UNCPath_AD-Group.yml | Queries AD for computer objects in a security group, builds a dynamic inventory, then deletes files older than N days from UNC paths on each server using an inline PowerShell function. | 16 |  |  |  |  | psscript | M | Inline PowerShell deletes files older than N days from UNC paths. Dynamically builds inventory from AD. Same AD-driven pattern as file-move — needs same Orchestrator approach for dynamic host discovery. | 1P_EMAT_file-deletion_with-UNCPath_AD-Group 1P_ConvergedL3_file-deletion_with-UNCPath_AD-Group | domain service account | WinRM_servers | Windows | PowerShell Host | No — Inline PowerShell; AD group DN and parameters supplied at runtime | Playbook: psscript/file-deletion_with-UNCPath_AD-Group.yml | 1P_EMAT_file-deletion_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-Monitoring-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\ccmcache file_filter: '*' days_old: '3' | 1P_ConvergedL3_file-deletion_with-UNCPath_AD-Group extra_vars: group_dn: CN=CVS-Converged-All-Servers,OU=Groups,OU=State Dept,DC=CONNECT,DC=SBU source_path: C$\Windows\ccmcache file_filter: '*' days_old: '-3'
18 | Medium | VMware_Disable_SSH.yml | Runs a PowerShell script against vCenter(s) to disable SSH on VMware hosts, with email reporting and vCenterList input. | 15 |  |  |  |  | psscript | M | PS script disables SSH on VMware hosts via PowerCLI. Despite being a VMware operation, runs through WinRM/PowerShell. Orchestrator alternative: use vCenter plugin to manage ESXi SSH service directly. | 1P_ConvergedL3_VMware_Disable_SSH | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/VMware_Disable_SSH.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_ConvergedL3_VMware_Disable_SSH extra_vars: var_ps_folder: ps_reports var_ps_script_file: cvs_report_script.ps1 var_parameter_action: VMware_Disable_SSH var_eMailReport: 'yes' var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: DTCVSOn-PremEngineering@state.gov var_MailCcString: DTCVSMonitoring@state.gov var_MailSubjectstring: 'Ansible-Report: VMware SSH Enabled Report' var_cleanup_temporary_folder: true var_vCenterList: >- esocoewvcs01.washdc.state.sbu, esoco26vcs01.washdc.state.sbu, esoco26vcs02.washdc.state.sbu, esocoewvcs.washdc.state.sbu, esocoewvcs02.washdc.state.sbu
19 | Medium | nexus_password_change.yml | Changes the admin password on Cisco Nexus switches. Constructs password from prefix + hostname + suffix, applies, saves, resets connection, verifies. | 13 |  |  |  |  | networking | M | Constructs password from prefix + hostname + suffix, applies via CLI, saves config, reconnects to verify with new credentials. Reconnect-and-verify needs careful handling — may need a second SSH session. | 1N_NET_HST_TEST-Switch_Change-Password 1N_NET_EW_Nex9k_Change_Password | ssh, ssh, gitlab | HST-TESTswitch-Nex9k-key, EW-Nex9k-key | Cisco NX-OS | SSH Connection | No | Playbook: networking/nexus_password_change.yml | 1N_NET_HST_TEST-Switch_Change-Password | 1N_NET_EW_Nex9k_Change_Password
20 | Medium | nexus_upgrades/upgrade_64.yml | Upgrades Nexus 9000v running 64-bit NX-OS (nxos64-cs), same nxos_install_os workflow but parses 64-bit filename convention. | 10 |  |  |  |  | networking | L | Uses nxos_install_os for 64-bit NX-OS upgrades. Involves reboot wait, SSH reset, version assertion. Long-running — Orchestrator needs appropriate timeouts and polling/wait for reboot completion. 5 templates. | 1N_NET_HST_Nex9k_Upgrade_10.3.8 1N_NET_EW_Nex9k_Upgrade_10.5.x 1N_NET_HST_Nex9k_Upgrade_10.5.x 1N_NET_MDC_Nex9k_Upgrade_10.5.x 1N_NET_HST_TESTSwitch_64_Upgrade | ssh | EW-Nex9k-key, HST-Nex9k-key, MDC-Nex9k-key, HST-TESTswitch-Nex9k-key | Cisco NX-OS | SSH Connection | No — Assumes {{new_image}} already staged in bootflash | Playbook: networking/nexus_upgrades/upgrade_64.yml | 1N_NET_HST_Nex9k_Upgrade_10.3.8 extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.4.M.bin | 1N_NET_EW_Nex9k_Upgrade_10.5.x extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.4.M.bin | 1N_NET_HST_Nex9k_Upgrade_10.5.x extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.5.M.bin | 1N_NET_MDC_Nex9k_Upgrade_10.5.x extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.5.M.bin | 1N_NET_HST_TESTSwitch_64_Upgrade extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.3.F.bin
21 | Medium | create_snmp_account.yml | Configures an SNMPv3 user on Cisco Nexus 9K switches with auth (SHA/MD5) and privacy (AES/DES) protocols. Validates inputs, applies config, verifies, and optionally sets contact/location. | 6 |  |  |  |  | networking | M | Configures SNMPv3 with auth/privacy protocols. Input validation for protocol types. Straightforward CLI config but needs proper input validation in Orchestrator form. | 1N_NET_HST_Nex9k_SNMP_Account_Create_9.3 1N_NET_HST_Nex9k_SNMP_Account_Create_Zabbix | ssh, ssh, domain service account for vCenter | NEXUS-9x constructed | Cisco NX-OS | SSH Connection | No | Playbook: networking/create_snmp_account.yml | 1N_NET_HST_Nex9k_SNMP_Account_Create_9.3 extra_vars: _groups: n9kv | 1N_NET_HST_Nex9k_SNMP_Account_Create_Zabbix extra_vars: _groups: n9kv
22 | Medium | workflow template |  | 6 | [5 empty] | S | AAP workflow template (not a playbook). Chains other job templates. In Orchestrator, maps to a workflow that calls sub-workflows. | 1A-Service-Account-PW-Changes | domain service account | WinRM_servers | Windows | PowerShell Host |  |  | 1A-Service-Account-PW-Changes
23 | Medium | clab_n9kv/backup.yml | Backs up running configs of Cisco network devices (N9kv/Cat9k) to a GitLab/Gitea repository in a timestamped branch via ansible.scm. Then dynamically creates AAP job templates for Diff and Restore playbooks with branch-selection surveys. | 5 |  |  |  |  | networking | XL | Most complex network playbook. Backs up configs to GitLab/Gitea via ansible.scm, then dynamically creates AAP job templates with surveys. Orchestrator needs: SSH for config retrieval, REST for Git API, and potentially Orchestrator API calls to create workflows dynamically. 6 templates across 3 sites. | 1N_NET_EW_Nex9k_backup_withkey 1N_NET_HST_Nex9k_backup-sshkey 1N_NET_MDC_Nex9k_backup 1N_NET_HST_Nex9k_backup 1N_NET_EW_Nex9k_backup 1N_NET_MDC_CAT_backup | ssh, gitlab, cisco cli, ssh, gitlab, ssh | EW-Nex9k-key, HST-Nex9k-key, MDC-Nex9k-key, HSX-Nex9k-key, MDC-Nex9k | Cisco NX-OS | SSH Connection, REST Host | Yes — Companion playbooks: diff.yml, restore.yml; requires GitLab/Gitea repo and AAP controller access | Playbook: networking/clab_n9kv/backup.yml Companion: networking/clab_n9kv/diff.yml Companion: networking/clab_n9kv/restore.yml | 1N_NET_EW_Nex9k_backup_withkey extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-EW ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: EW-Nex9k-key ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: 1N-L3-EW-Network-Git-n9kv-Diff job_template_restore: 1N-L3-EW-Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git | 1N_NET_HST_Nex9k_backup-sshkey extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-MDC ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: HST-Nex9k ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: Network-Git-n9kv-Diff job_template_restore: Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git | 1N_NET_MDC_Nex9k_backup extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-MDC ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: MDC-Nex9k-key ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: Network-Git-n9kv-Diff job_template_restore: Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git | 1N_NET_HST_Nex9k_backup extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-MDC ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: HST-Nex9k ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: Network-Git-n9kv-Diff job_template_restore: Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: cvsgit.washdc.state.sbu/cvs/network.git | 1N_NET_EW_Nex9k_backup extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-MDC ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: EW-Nex9k-key ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: Network-Git-n9kv-Diff job_template_restore: Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: cvsgit.washdc.state.sbu/cvs/network.git | 1N_NET_MDC_CAT_backup extra_vars: aap_cred: cvs-AAP-AT gitlab_cred: cvs-Gitlab-AT cisco_cred: admin@cisco-MDC ansible_organization: cvs ansible_project: 1N_Network-Project ansible_inventory: MDC-Nex9k-key ansible_ee: ee-supported-rhel9 gitlab_project: network job_template_diff: Network-Git-n9kv-Diff job_template_restore: Network-Git-n9kv-Restore play_dir: clab_n9kv dir_path: /tmp/{{gitlab_project}}/network_backup_files git_url: cvsgit.washdc.state.sbu/cvs/network.git
24 | Medium | playbooks/satellite/dnf_update.yml | Runs 'dnf upgrade -y' on all targeted Linux hosts. | 1 |  |  |  |  | admins | S | Simply runs dnf upgrade -y. One of the easiest conversions — single SSH command. 4 templates differ only by inventory targeting. | 1A_DNF_update-EW 1A_DNF_update 1A_DNF_update-HST 1A_DNF_update-Dynatrace | ssh | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection | No | Playbook: admins/playbooks/satellite/dnf_update.yml | 1A_DNF_update-EW | 1A_DNF_update | 1A_DNF_update-HST | 1A_DNF_update-Dynatrace
25 | Medium | firewall_rich_rule.yml | Configures RHEL 9 firewalld to restrict a service to specific IPs/subnets via rich rules, with input validation and admin-IP safety checks. | 1 |  |  |  |  | rhel | M | Configures firewalld rich rules with input validation and admin-IP safety checks. Multiple sequential firewall-cmd calls with rollback logic. Safety check to prevent lockout is critical — do not omit. | 1R_EMAT_firewall_Ansible-AllowPort?? 1R_EMAT_firewall_rich_rule-P22 1R_EMAT_firewall_rich_rule-P8445 1R_EMAT_firewall_rich_rule-P27199 | ssh | Ansible System, Dynatrace System | RHEL | SSH Connection | No | Playbook: rhel/firewall_rich_rule.yml | 1R_EMAT_firewall_Ansible-AllowPort?? extra_vars: service_to_remove: ssh service_port: 8445 admin_ips: - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 allowed_ssh_ips: - 10.7.43.99 - 10.7.42.230 - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 | 1R_EMAT_firewall_rich_rule-P22 extra_vars: service_to_remove: ssh service_port: 22 admin_ips: - 10.7.42.230 - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 - 10.82.0.31 allowed_ssh_ips: - 10.7.42.230 - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.187.91 - 10.68.187.92 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 - 10.3.128.169 - 10.3.128.171 - 10.20.33.100 - 110.68.6.82 - 10.87.130.41 - 10.87.130.42 - 10.87.130.43 - 10.87.130.44 - 10.87.130.45 - 10.87.130.46 - 10.68.6.72 - 10.68.6.73 - 10.3.128.162 - 10.3.128.163 - 10.20.33.92 - 10.20.33.93 - 10.68.85.5 - 10.68.85.6 - 10.65.13.25 - 10.65.13.26 - 10.68.187.0/24 - 10.3.97.0/24 - 10.65.88.0/24 - 10.64.34.0/24 - 10.7.42.0/23 | 1R_EMAT_firewall_rich_rule-P8445 extra_vars: service_to_remove: ssh service_port: 8445 admin_ips: - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 allowed_ssh_ips: - 10.7.42.230 - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 | 1R_EMAT_firewall_rich_rule-P27199 extra_vars: service_to_remove: ssh service_port: 27199 admin_ips: - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79 allowed_ssh_ips: - 10.7.42.230 - 10.3.128.164 - 10.3.128.165 - 10.3.128.166 - 10.20.33.95 - 10.20.33.96 - 10.20.33.97 - 10.68.6.77 - 10.68.6.78 - 10.68.6.79
26 | Low | clab_n9kv/restore.yml | Restores Nexus 9000 configurations from a GitLab/Gitea branch. Copies saved config to bootflash, runs configure replace, then cleans up the temp file. | 0 |  |  |  |  | networking | L | Restores configs from Git branch. Copies saved config to bootflash, runs configure replace. Companion to backup.yml — needs Git API access. 3 templates per site. | 1N-L3-EW-Network-Git-n9kv-Restore Network-Git-n9kv-Restore 1N-ConvergedL3-EW-Network-Git-n9kv-Restore | ssh, cisco cli, gitlab, Ansible Platform | EW-Nex9k-key, MDC-Nex9k-key | Cisco NX-OS | SSH Connection, REST Host | Yes — External: Git repo at {{git_url}} (config files in network_backup_files/) | Playbook: networking/clab_n9kv/restore.yml File: networking/files/) External: Git repository ({{git_url}}) | 1N-L3-EW-Network-Git-n9kv-Restore extra_vars: git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git dir_path: /tmp/network/network_backup_files gitlab_project: network | Network-Git-n9kv-Restore extra_vars: git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git dir_path: /tmp/network/network_backup_files gitlab_project: network | 1N-ConvergedL3-EW-Network-Git-n9kv-Restore extra_vars: git_url: cvsgit.washdc.state.sbu/cvs/network.git dir_path: /tmp/network/network_backup_files gitlab_project: network
27 | Low | clab_n9kv/diff.yml | Compares running Nexus 9000 configurations against a saved config in a GitLab/Gitea branch using nxos_config diff_against: intended. Used by the backup.yml-generated job template. | 0 |  |  |  |  | networking | L | Compares running config against Git-stored config using nxos_config diff. Companion to backup.yml. Needs Git API access for saved config retrieval. | Network-Git-n9kv-Diff 1N-L3-EW-Network-Git-n9kv-Diff | cisco cli, gitlab, Ansible Platform | MDC-Nex9k-key, EW-Nex9k-key | Cisco NX-OS | SSH Connection, REST Host | Yes — External: Git repo at {{git_url}} (config files in network_backup_files/) | Playbook: networking/clab_n9kv/diff.yml File: networking/files/) External: Git repository ({{git_url}}) | Network-Git-n9kv-Diff extra_vars: git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git dir_path: /tmp/network/network_backup_files gitlab_project: network | 1N-L3-EW-Network-Git-n9kv-Diff extra_vars: git_url: gitmgitlab01.washdc.state.sbu/conus-automation/network.git dir_path: /tmp/network/network_backup_files gitlab_project: network
28 | Low | aria_operations_firewall.yml | Comprehensive VMware Aria 8.18 iptables firewall hardening. Backs up rules, removes blanket ACCEPT/REJECT rules from INPUT/TCP/UDP chains, adds cluster-node allow rules, adds per-port allow rules for specified networks/IPs, adds catch-all DROP to TCP/UDP chains, persists via systemd service + rc.local + cron @reboot. | 0 |  |  |  |  | aria | L | Complex iptables hardening: backs up rules, removes blanket ACCEPT/REJECT, adds cluster-node and per-port allow rules, catch-all DROP, persists via systemd + rc.local + cron. HIGH RISK of lockout if implemented incorrectly. Test thoroughly in lab. | 2A_EMAT_Aria-Operations_Firewall_ProxyServers 2A_EMAT_Aria-Operations_Firewall_Cluster | ssh | vROPS System | Aria (Photon OS) | SSH Connection | No | Playbook: aria/aria_operations_firewall.yml | 2A_EMAT_Aria-Operations_Firewall_ProxyServers | 2A_EMAT_Aria-Operations_Firewall_Cluster
29 | Low | create_RHEL_local.yml | Creates a local user account on RHEL hosts with a password (SHA512 hashed), adds to wheel group. Simpler than the password-change playbook — no complexity validation or backup. | 0 |  |  |  |  | admins | S | Creates local user with SHA512 password hash, adds to wheel. Very simple — 2-3 SSH commands. | 1A_create_RHEL_local_account | ssh | Postgres system | RHEL | SSH Connection | No | Playbook: admins/create_RHEL_local.yml | 1A_create_RHEL_local_account
30 | Low | PowerFlex_SUSE15-V2R5-PasswordPolicy.yml | Applies the SUSE 15 STIG V2R5 password policy role to PowerFlex hosts. | 0 |  |  |  |  | stig | L | STIG password policy role for PowerFlex SLES 15. Role contains dozens of individual tasks. Consider replicating task-by-task or using a single script. | 1S_ConvergedL3_STIG_PFX_Password-Policy |  | PFX | SLES | SSH Connection | Yes — Role: roles/PowerFlex_SUSE15-PasswordPolicy/ | Playbook: stig/PowerFlex_SUSE15-V2R5-PasswordPolicy.yml Role: stig/roles/PowerFlex_SUSE15-PasswordPolicy/ | 1S_ConvergedL3_STIG_PFX_Password-Policy
31 | Low | STIG_PFM-SLES15.yml | Combined PowerFlex SLES 15 STIG role application; a wrapper that applies the full PowerFlex SUSE 15 STIG role. | 0 |  |  |  |  | stig | XL | Full PowerFlex SLES 15 STIG — combined wrapper for all categories. 100+ individual tasks. Consider breaking into sub-workflows per STIG category or a monolithic script. | 1S_ConvergedL3_STIG_PFX_General 1S_ConvergedL3_STIG_PFX_General_OW |  | PFX | SLES | SSH Connection | Yes — Role: roles/PowerFlex_SUSE15/ | Playbook: stig/STIG_PFM-SLES15.yml Role: stig/roles/PowerFlex_SUSE15/ | 1S_ConvergedL3_STIG_PFX_General | 1S_ConvergedL3_STIG_PFX_General_OW
32 | Low | PowerFlex_SUSE15-V2R5-Banner.yml | Applies the SUSE 15 STIG V2R5 login banner role to PowerFlex (SLES 15) hosts. | 0 |  |  |  |  | stig | S | Applies login banner. Simple file content replacement — one of the easier STIG items. | 1S_ConvergedL3_STIG_PFX_Banner |  | PFX | SLES | SSH Connection | Yes — Role: roles/PowerFlex_SUSE15-Banner/ | Playbook: stig/PowerFlex_SUSE15-V2R5-Banner.yml Role: stig/roles/PowerFlex_SUSE15-Banner/ | 1S_ConvergedL3_STIG_PFX_Banner
33 | Low | mde_gcc_install.yml | Installs Microsoft Defender for Endpoint on RHEL (GCC environment variant). Installs yum-utils, stops fapolicyd if present, copies the GCC onboarding script, runs the Python onboarding, restarts mdatp, and re-enables fapolicyd. | 0 |  |  |  |  | dev | M | Installs MDE (GCC variant). Copies onboarding scripts, runs Python installer, manages fapolicyd. External scripts must be accessible to Orchestrator host or embedded as resource elements. | 1D_DEV_MDE_GCC_RHEL_Install | ssh | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection | Yes — Files: files/mde_gcc/mde_gcc_install.sh, files/mde_gcc/MicrosoftDefenderATPOnboardingLinuxServer.py | Playbook: dev/mde_gcc_install.yml File: dev/files/mde_gcc/mde_gcc_install.sh File: dev/files/mde_gcc/MicrosoftDefenderATPOnboardingLinuxServer.py | 1D_DEV_MDE_GCC_RHEL_Install
34 | Low | files/powerflex/pf_update_credentials_by_label.yml | Updates credentials in the PowerFlex Manager credential store by exact label match. Fetches credentials by label via API filtering, supports type filtering and dry-run mode. Includes active PUT calls for live updates (XML body format). | 0 |  |  |  |  | dev | M | REST API calls to PowerFlex Manager. Auth, fetch by label, PUT with XML body. Use Orchestrator REST plugin. Supports dry-run mode. | 1D_EMAT_powerflex_cred_update_ByLabel |  | aap controller | PowerFlex Manager | REST Host | No | Playbook: dev/files/powerflex/pf_update_credentials_by_label.yml | 1D_EMAT_powerflex_cred_update_ByLabel
35 | Low | files/powerflex/pf_credential_update.yml | Updates credentials in the PowerFlex Manager credential store by name pattern. Authenticates via REST API, fetches all credentials, filters by include/exclude name patterns and optional type filter, supports dry-run mode. Update PUT calls are commented out (ready to enable). | 0 |  |  |  |  | dev | M | Similar to pf_update_credentials_by_label but filters by name regex. PUT calls commented out (ready to enable). Same REST plugin approach. | 1D_EMAT_powerflex_cred_update |  | aap controller | PowerFlex Manager | REST Host | No | Playbook: dev/files/powerflex/pf_credential_update.yml | 1D_EMAT_powerflex_cred_update
36 | Low | files/powerflex/pf_list_all_cred_types.yml | Queries the PowerFlex Manager API and lists all unique credential type names (e.g., OSCredential, ServerCredential). Used to discover correct API type names for filtering in credential update playbooks. | 0 |  |  |  |  | dev | S | Simple REST GET to list credential types. Read-only. Good first PowerFlex conversion to learn the REST pattern. | 1D_EMAT_powerflex_List_All_Credential_Types |  | aap controller | PowerFlex Manager | REST Host | No | Playbook: dev/files/powerflex/pf_list_all_cred_types.yml | 1D_EMAT_powerflex_List_All_Credential_Types
37 | Low | files/powerflex/pf_check_managed_resources.yml | Queries the PowerFlex Manager API for deployed services and managed/unmanaged resource groups. Generates a detailed report indicating whether actual host password updates are supported (deployed/managed) or only credential-store updates (discovered/unmanaged). | 0 |  |  |  |  | dev | S | REST GET to check deployed services and managed resources. Read-only report. Good starter for REST pattern. | 1D_EMAT_powerflex_check_managed_resources |  | aap controller | PowerFlex Manager | REST Host | No | Playbook: dev/files/powerflex/pf_check_managed_resources.yml | 1D_EMAT_powerflex_check_managed_resources
38 | Low | esxi-stig.yml | VMware vSphere 8.0 ESXi STIG remediation playbook. Validates vCenter connectivity, discovers ESXi hosts by hostname list or cluster, loads production STIG config from a YAML file, then applies security, logging, services, and reporting roles. Supports both individual host and cluster-wide targeting. | 0 |  |  |  |  | esxi-stig | XL | Largest VMware playbook. 4 roles (security, logging, services, reporting) with dozens of tasks each. Needs vCenter plugin (host discovery) + SSH (ESXi shell). Break into sub-workflows per STIG category. | 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS01 1E-ConvergedL3-ESXI-STIG@ESOCO26VCS01 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS02 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS | ssh, ssh, domain service account for vCenter | aap controller | vCenter/ESXi | vCenter Plugin, SSH Connection | Yes — Roles: roles/vsphere_stig_security/, roles/vsphere_stig_logging/, roles/vsphere_stig_services/, roles/vsphere_stig_reporting/; File: config/production_stig_config.yml | Playbook: esxi-stig/esxi-stig.yml Role: esxi-stig/roles/vsphere_stig_security/ Role: esxi-stig/roles/vsphere_stig_logging/ Role: esxi-stig/roles/vsphere_stig_services/ Role: esxi-stig/roles/vsphere_stig_reporting/ Config: esxi-stig/config/production_stig_config.yml | 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS01 | 1E-ConvergedL3-ESXI-STIG@ESOCO26VCS01 | 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS02 | 1E-ConvergedL3-ESXI-STIG@ESOCOEWVCS
39 | Low | esxi_port_test.yml | Dynamically discovers ESXi hosts in specified vCenter clusters via community.vmware, then runs port connectivity tests against them using an included task file. | 0 |  |  |  |  | admins | M | Two-phase: discovers ESXi hosts via vCenter API, then runs port tests. External task file dependency. | 1A_Port-Test_ESXi-esocoewvcs02-01-ESOC-VXRAIL | ssh, domain service account | aap controller | vCenter/ESXi | vCenter Plugin, SSH Connection | Yes — Task file: tasks/get_esxi_inventory.yml | Playbook: admins/esxi_port_test.yml Task: admins/tasks/get_esxi_inventory.yml | 1A_Port-Test_ESXi-esocoewvcs02-01-ESOC-VXRAIL extra_vars: var_datacenter_name: 01-ESOC-VXRAIL var_cluster_name: - VXRL-Cluster01-Staging var_test_port: - 22 - 443 - 80
41 | Low | TLS-fix.yml | Runs a PowerShell script on Windows hosts with Action, ActionRemoteFile, ADGroupMember, and DomainName parameters for TLS remediation. | 0 |  |  |  |  | psscript | M | External PS script for TLS remediation. 5 templates. Could potentially be replaced by direct registry manipulation in Orchestrator PowerShell tasks. | 1P_EMAT_Server_TLS_Fix 1P_DPT_Server_TLS_Fix 1P_DPT_Server_TLS_Fix_v2 1P_SEC_Server_TLS_Fix 1P_ConvergedL3_Server_TLS_Fix | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/TLS-fix.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_EMAT_Server_TLS_Fix extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: tls-fix var_parameter_actionRemoteFile: DisableAll-N-Enable-TlsCipherSuite.ps1 var_DomainName: connect.sbu var_OUPath: OU=Groups,OU=State Dept,DC=connect,DC=sbu var_cleanup_temporary_folder: false var_ADGroupMember: CVS-Monitoring-Servers | 1P_DPT_Server_TLS_Fix extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: tls-fix var_parameter_actionRemoteFile: Disable-TlsCipherSuite.ps1 var_OUPath: '' var_cleanup_temporary_folder: false var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-DPT-AllServers | 1P_DPT_Server_TLS_Fix_v2 extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: tls-fix var_parameter_actionRemoteFile: Disable-TlsCipherSuiteV2.ps1 var_OUPath: '' var_cleanup_temporary_folder: false var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-DPT-MgmtServers | 1P_SEC_Server_TLS_Fix extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: tls-fix var_parameter_actionRemoteFile: Disable-TlsCipherSuite.ps1 var_OUPath: '' var_cleanup_temporary_folder: false var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-Security-Servers | 1P_ConvergedL3_Server_TLS_Fix extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_parameter_action: tls-fix var_parameter_actionRemoteFile: Disable-TlsCipherSuite.ps1 var_OUPath: '' var_cleanup_temporary_folder: false var_DomainName: washdc.state.sbu var_ADGroupMember: CVS-ConvergedL3-TEST-Servers
42 | Low | PowerFlex_SUSE15-V2R5-Logging.yml | Applies the SUSE 15 STIG V2R5 logging configuration role to PowerFlex hosts. | 0 |  |  |  |  | stig | L | STIG logging role for PowerFlex SLES. Multiple rsyslog/auditd tasks. Role-based — review full role directory. | 1S_ConvergedL3_STIG_PFX_Log-Policies |  | PFX | SLES | SSH Connection | Yes — Role: roles/PowerFlex_SUSE15-Logging/ | Playbook: stig/PowerFlex_SUSE15-V2R5-Logging.yml Role: stig/roles/PowerFlex_SUSE15-Logging/ | 1S_ConvergedL3_STIG_PFX_Log-Policies
43 | Low | ansible_post_stig.yml | Applies the ansible_post_stig role to remediate or verify post-STIG configuration items on all targeted hosts. | 0 |  |  |  |  | stig | L | Post-STIG remediation role. Fixes items needing adjustment after main STIG pass. Review roles/ansible_post_stig/ for full task list. | 1S_EMAT-Ansible-System-STIG-POST | domain service account | WinRM_servers | RHEL | SSH Connection | Yes — Role: roles/ansible_post_stig/ | Playbook: stig/ansible_post_stig.yml Role: stig/roles/ansible_post_stig/ | 1S_EMAT-Ansible-System-STIG-POST
44 | Low | admin_accounts_report.yml | Runs a PowerShell script to report on admin accounts from a specified AD OU path, with email delivery and debug output. | 0 |  |  |  |  | psscript | M | V1 of admin accounts report. Superseded by v2. Consider retiring during conversion rather than converting both. | 1P_SEC_Admin_Accounts_Status 1P_SEC_Admin_Accounts_Status-WHA 1P_SEC_Admin_Accounts_Status-WASHDC | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Files: files/{{var_ps_folder}}/{{var_ps_script_file}} | Playbook: psscript/admin_accounts_report.yml File: psscript/files/{{var_ps_folder}}/{{var_ps_script_file}} | 1P_SEC_Admin_Accounts_Status extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: >- DTHISecurityFL@state.gov,DT-CVS-Data-Protection-Team-FL@state.gov,DTCVSOn-PremEngineering@state.gov var_MailCcString: >- amsaem@state.gov,esocsecurityteam@state.gov,DTCVSMonitoring@state.gov,DTHISecurityFL@state.gov var_MailSubjectstring: 'Ansible-Report: CVS Admin PKI Card Status' var_DomainName: washdc.state.sbu var_OUPath: OU=Admin Accounts,OU=ESOC,OU=M,OU=IRM,DC=washdc,DC=state,DC=sbu | 1P_SEC_Admin_Accounts_Status-WHA extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: CVS OCONUS(WHA) - Admin PKI Card Status' var_DomainName: wha.state.sbu var_OUPath: >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=wha,DC=state,DC=sbu | 1P_SEC_Admin_Accounts_Status-WASHDC extra_vars: var_ps_folder: ps_scripts var_ps_script_file: cvs_functions.ps1 var_eMailReport: 'yes' var_parameter_action: Get-AllAdmin-Accounts var_SMTPServer: nccsmtprelay.irm.state.gov var_MailToString: nguyentd4@state.gov var_MailCcString: nguyentd4@state.gov var_MailSubjectstring: 'Ansible-Report: CVS OCUNUS (WASHDC) - Admin PKI Card Status' var_DomainName: washdc.state.sbu var_OUPath: >- OU=GITM VG,OU=Admin Accounts,OU=GITM,OU=Domain Management,OU=AD Management,DC=washdc,DC=state,DC=sbu
45 | Low | nexus_upgrades/staging.yml | Stages firmware to Cisco Cat8000v routers: enables SCP, fetches image from backup server, copies to bootflash via net_put, verifies SHA512 hash. | 0 |  |  |  |  | networking | L | Basic firmware staging without pre-flight checks. Simpler than staging-with-scp but still involves SCP + SHA512. Consider converting only the enhanced version and retiring this one. | 1N_NET_n9kv_Staging | ssh | cisco | Cisco NX-OS | SSH Connection | Yes — External file: ~/upgrades/{{new_image}} on backup-server | Playbook: networking/nexus_upgrades/staging.yml External: SCP file on remote server | 1N_NET_n9kv_Staging extra_vars: _groups: n9kv new_image: nxos64-cs.10.4.5.M.bin remote_file: /var/lib/podme/upgrades/{{ new_image }} remote_scp_server: 10.20.33.95 vrf: default sha_hash: >- 2b51f7ca822ad64a142e4f29a11973e5d59b728e09a408478305057cc4303f53324f12968c37b9476b22e0c152c9897177c265ff8cda01390618c3605f9d978f
46 | Low | mde_rhel_install.yml | Full MDE installation on RHEL: installs yum-utils, stops fapolicyd, copies and runs the onboarding Python script, backs up the onboarding JSON, executes the installer shell script, then restarts fapolicyd. | 0 |  |  |  |  | dev | M | Full MDE install with external shell/Python scripts. Manages fapolicyd around installation. Scripts need to be accessible from Orchestrator. | 1D_DEV_MDE_RHEL_Install |  | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection | Yes — Files: files/mde/mde_installer-AV-active-S9.4.sh, files/mde/MicrosoftDefenderATPOnboardingLinuxServer.py | Playbook: dev/mde_rhel_install.yml File: dev/files/mde/mde_installer-AV-active-S9.4.sh File: dev/files/mde/MicrosoftDefenderATPOnboardingLinuxServer.py | 1D_DEV_MDE_RHEL_Install
47 | Low | mde_rhel_post_install.yml | Similar to the health check but expects real-time protection to be false (passive mode). Used for post-install verification before enabling active protection. | 0 |  |  |  |  | dev | S | Post-install verification only (passive mode check). Runs mdatp commands and checks output. Simple command-and-assert. | 1D_DEV_MDE_RHEL_POST_Install | ssh (sudo) | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection | No | Playbook: dev/mde_rhel_post_install.yml | 1D_DEV_MDE_RHEL_POST_Install
48 | Low | mde_rhel_health_check.yml | Post-install MDE health validation: checks org_id, healthy status, real-time protection (expects true), and connectivity test (expects ≥10 OK endpoints), asserting each against expected values. | 0 |  |  |  |  | admins, dev | S | Health check — mdatp commands with assertions. Simple command-and-assert. 2 templates differ by auth method. | 1D_DEV_MDE_RHEL_Health_check 1D_DEV_MDE_RHEL_Health_check_via_ansible_Key | ssh | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection | No | Playbook: admins/mde_rhel_health_check.yml | 1D_DEV_MDE_RHEL_Health_check | 1D_DEV_MDE_RHEL_Health_check_via_ansible_Key
49 | Low | rhel_change_root_pw.yml | Enterprise-grade RHEL password change for AAP 2.5 surveys. Password complexity validation, self-lockout protection, shadow backup, SHA512 hashing, aging policy, audit logging, emergency rollback. | 0 |  |  |  |  | admins | L | Enterprise password change with extensive validation: complexity checks, confirmation, self-lockout protection, shadow backup with cleanup, SHA512, aging policy, audit logging, emergency rollback. Do not simplify the safety checks. | 1A_Update-RHEL-Root-PW | ssh | Dynatrace System | RHEL | SSH Connection | No | Playbook: admins/rhel_change_root_pw.yml | 1A_Update-RHEL-Root-PW
50 | Low | rhel9STIG_03.2024.yml | Applies a STIG hardening role to RHEL 9 hosts, with the role name passed as a variable (var_role). | 0 |  |  |  |  | stig | XL | Full RHEL 9 STIG role (role name at runtime). Hundreds of tasks. Consider sub-workflows or monolithic script. | 1S_EMT_AutomationSystem_STIG_RHEL9_3.2024 | ssh | Ansible System | RHEL | SSH Connection | Yes — Role: roles/{{var_role}}/ (role name supplied at runtime via extra vars) | Playbook: stig/rhel9STIG_03.2024.yml Role: stig/roles/{{var_role}}/ | 1S_EMT_AutomationSystem_STIG_RHEL9_3.2024
51 | Low | rhel8STIG_V2R3.yml | Applies the RHEL 8 STIG V2R3 hardening role to all targeted hosts. | 0 |  |  |  |  | stig | XL | Full RHEL 8 STIG V2R3 role. Hundreds of tasks. Currently targets Zabbix systems only. | 1S_EMAT-Zabbix-System-STIG-V2R3 | ssh | Zabbix_System | RHEL | SSH Connection | Yes — Role: roles/rhel8STIG_V2R3/ | Playbook: stig/rhel8STIG_V2R3.yml Role: stig/roles/rhel8STIG_V2R3/ | 1S_EMAT-Zabbix-System-STIG-V2R3
53 | Low | playbooks/satellite/registry_to_satellite.yml | Registers RHEL 9 systems with Red Hat Satellite/Foreman: unregisters, cleans caches, calls registration API with activation key, verifies repositories. | 0 |  |  |  |  | admins | M | Unregisters existing subscriptions, cleans caches, calls Satellite registration API via curl. Curl call could be replaced with Orchestrator REST operation. 3 templates per site. | 1A_Satellite_HST_registration 1A_Satellite_EW_registration 1A_Satellite_MDC_registration | ssh | Install-MDE-Target-RHEL-Devices | RHEL | SSH Connection, REST Host | No | Playbook: admins/playbooks/satellite/registry_to_satellite.yml | 1A_Satellite_HST_registration extra_vars: foreman_server: cvsoowsat01.washdc.state.sbu foreman_port: '443' foreman_protocol: https activation_keys: ak_rhel9.6 hostgroup_id: '2' location_id: '2' operatingsystem_id: '1' organization_id: '1' update_packages: 'false' bearer_token: >- eyJhbGciOiJIUzI1NiJ9.eyJ1c2VyX2lkIjo0LCJpYXQiOjE3NjQ4Mzc5ODAsImp0aSI6IjllMDBhMzU2NTRiYzc4NjQ5NDA4ODA2Yjg0YzQ3MDRlODEwMWFiNzk1Y2FjYTJlNTNjODFhNjBjY2FkYmFjYzMiLCJzY29wZSI6InJlZ2lzdHJhdGlvbiNnbG9iYWwgcmVnaXN0cmF0aW9uI2hvc3QifQ.yMvm0srswDyKJqxWnWCMWUQjUVk7BjImWpEF5Vxc_mM ssl_verify: false | 1A_Satellite_EW_registration extra_vars: foreman_server: cvsoewsat01.washdc.state.sbu foreman_port: '9090' foreman_protocol: https activation_keys: ak_rhel9.6 hostgroup_id: '8' location_id: '2' operatingsystem_id: '1' organization_id: '1' update_packages: 'false' bearer_token: >- eyJhbGciOiJIUzI1NiJ9.eyJ1c2VyX2lkIjo0LCJpYXQiOjE3NjQ4Nzk0ODIsImp0aSI6IjY4YjkwZjE4YWI4ZjFkMDMzNjMyZjM4NTcwNzk4OTI0YjhlNDc4NzVlMjM1ZDJiNDEyMjk3ZGU5ODVhZGQyZjYiLCJzY29wZSI6InJlZ2lzdHJhdGlvbiNnbG9iYWwgcmVnaXN0cmF0aW9uI2hvc3QifQ.ACv5dN5MnR2WtoxWxfZZgNYiK2k2B6zlfZpwf9W4l8k ssl_verify: false | 1A_Satellite_MDC_registration extra_vars: foreman_server: cvso26sat01.washdc.state.sbu foreman_port: '9090' foreman_protocol: https activation_keys: ak_rhel9.6 hostgroup_id: '4' location_id: '2' operatingsystem_id: '1' organization_id: '1' update_packages: 'false' bearer_token: >- eyJhbGciOiJIUzI1NiJ9.eyJ1c2VyX2lkIjo0LCJpYXQiOjE3NjQ4NTc2NzUsImp0aSI6IjIyMWFiNzMzYzUzZDdjMTA1ZjUzMTAxNTk5NDhlMDU2MjY0MmU1YmUwOGM0ZTZiNzIzZmM5MzQwYzI5NTRlNjYiLCJzY29wZSI6InJlZ2lzdHJhdGlvbiNnbG9iYWwgcmVnaXN0cmF0aW9uI2hvc3QifQ.OUhsuX9VE8MfNc1yoXSj7MrU0WilaW6EHzf4Wttf6_U ssl_verify: false
54 | Low | nexus_upgrades/upgrade.yml | Upgrades Cisco Cat8000v: changes boot system, renames old packages.conf, runs install add file activate commit, waits for reboot, asserts new version. | 0 |  |  |  |  | networking | L | Standard NX-OS upgrade (non-64-bit). Changes boot system, install add file activate commit, reboot wait. Same long-running challenges as upgrade_64. 3 templates. | 1N_NET_EW_Nex9k_Upgrade_10.x 1N_NET_HST_Nex9k_Upgrade_9.3.15 1N_NET_MDC_Nex9k_Upgrade | ssh | EW-Nex9k-key, HST-Nex9k, MDC-Nex9k-key | Cisco NX-OS | SSH Connection | No — Assumes {{new_image}} already staged in bootflash | Playbook: networking/nexus_upgrades/upgrade.yml | 1N_NET_EW_Nex9k_Upgrade_10.x extra_vars: _groups: n9kv new_image: nxos64-cs.10.5.4.M.bin | 1N_NET_HST_Nex9k_Upgrade_9.3.15 extra_vars: _groups: n9kv new_image: nxos.9.3.15.bin | 1N_NET_MDC_Nex9k_Upgrade extra_vars: _groups: n9kv new_image: nxos.9.3.15.bin
55 | Low | new_user_key/set_user_key.yml | Creates a local user account on Nexus 9000 switches with an SSH public key and role, saves config. | 0 |  |  |  |  | networking | S | Creates local user with SSH key and role on Nexus switches. Simple CLI config + write mem. 2 templates. | Digital-Twin-N9kv-New-User-Key 1N_NET_HST-N9kv-New-User-Key | cisco cli, cisco cli, ssh | cisco, HSX-Nex9k | Cisco NX-OS | SSH Connection | No — SSH key passed via {{ssh_key}} variable | Playbook: networking/new_user_key/set_user_key.yml | Digital-Twin-N9kv-New-User-Key extra_vars: _groups: n9kv pub_key: ansiblelocal.pub folder: /tmp/.ssh/ localAccountname: ansiblelocal role: network-admi | 1N_NET_HST-N9kv-New-User-Key extra_vars: _groups: n9kv scp_server: cvsoowans11.washdc.state.sbu pub_key: ansiblelocal_pub folder: /var/cvs-scp/ localAccountname: ansiblelocal role: network-admin ssh_key: >- ssh-rsa AAAAB3NzaC1yc2EAAAADAQABAAABgQCp7H6UFefv+et/RE7ON9iDEC5pUj9WN2sfQIa6aAR7boG/w8m1v3vjL2WT4UL05EK5WGFYazGXPY1xi3TCYdFD9C+HZNziVCZUeBSPNs7kW2NAa1xWZMeUWCg9lubTVrYrfvUthoqgy6eifMgYkz69yRh1i86ZDRqmLI09IZvNN8BasL+Bdvpy3q1O7RCSpGMfVza4uANhwY8xjUzgCYwClf1dE9I+I7NewMN7o5lhXKXB0SEPj1I/vlaPnnZftd1R+0L5XY8t4R0gejvaD5H2Njb+KADpGT4pTErvvttzgmFFCirTfhIjTDmlaJNMScqIAAO+aUXPvTi5vRhCuRbWIDpIlKshwaZocNoRpW7EF3tCfIf3mvNDEvKI3txhmWyEZHvf4usV/5s4mo9+pGDRE6JwU3elQjmCjsx1R4vZbqKbArT75tN2TDMDnfymFGkb8lMI+m+kLx3qCYYk2HYG1hTYnb0FX84sEuo/W5ZgnfzUb1QNu2b00CMxP2W3i1s=
56 | Low | setup-ansible-vROPS-user.yml | Creates an Ansible service account on Linux hosts: user/group, wheel membership, SSH public key, passwordless sudo, ensures SSHD running. | 0 |  |  |  |  | admins | S | Creates service account: user/group, wheel, SSH key, passwordless sudo. Simple sequential SSH commands. 2 templates target vROPS and vCenters. | 1A_Add-Ansible-Account-forvROPS 1A_Add-Ansible-Account-forvCenters | root (prompted) | vROPS System, vCenters | Aria (Photon OS), vCenter (VCSA) | SSH Connection | No — SSH key passed via {{var_pub_key}} variable | Playbook: admins/setup-ansible-vROPS-user.yml | 1A_Add-Ansible-Account-forvROPS extra_vars: var_new_user: ansiblelocal var_pub_key: >- ssh-rsa AAAAB3NzaC1yc2EAAAADAQABAAABgQCp7H6UFefv+et/RE7ON9iDEC5pUj9WN2sfQIa6aAR7boG/w8m1v3vjL2WT4UL05EK5WGFYazGXPY1xi3TCYdFD9C+HZNziVCZUeBSPNs7kW2NAa1xWZMeUWCg9lubTVrYrfvUthoqgy6eifMgYkz69yRh1i86ZDRqmLI09IZvNN8BasL+Bdvpy3q1O7RCSpGMfVza4uANhwY8xjUzgCYwClf1dE9I+I7NewMN7o5lhXKXB0SEPj1I/vlaPnnZftd1R+0L5XY8t4R0gejvaD5H2Njb+KADpGT4pTErvvttzgmFFCirTfhIjTDmlaJNMScqIAAO+aUXPvTi5vRhCuRbWIDpIlKshwaZocNoRpW7EF3tCfIf3mvNDEvKI3txhmWyEZHvf4usV/5s4mo9+pGDRE6JwU3elQjmCjsx1R4vZbqKbArT75tN2TDMDnfymFGkb8lMI+m+kLx3qCYYk2HYG1hTYnb0FX84sEuo/W5ZgnfzUb1QNu2b00CMxP2W3i1s= enable_passwordless_sudo: true | 1A_Add-Ansible-Account-forvCenters extra_vars: var_new_user: ansiblelocal var_pub_key: >- ssh-rsa AAAAB3NzaC1yc2EAAAADAQABAAABgQCp7H6UFefv+et/RE7ON9iDEC5pUj9WN2sfQIa6aAR7boG/w8m1v3vjL2WT4UL05EK5WGFYazGXPY1xi3TCYdFD9C+HZNziVCZUeBSPNs7kW2NAa1xWZMeUWCg9lubTVrYrfvUthoqgy6eifMgYkz69yRh1i86ZDRqmLI09IZvNN8BasL+Bdvpy3q1O7RCSpGMfVza4uANhwY8xjUzgCYwClf1dE9I+I7NewMN7o5lhXKXB0SEPj1I/vlaPnnZftd1R+0L5XY8t4R0gejvaD5H2Njb+KADpGT4pTErvvttzgmFFCirTfhIjTDmlaJNMScqIAAO+aUXPvTi5vRhCuRbWIDpIlKshwaZocNoRpW7EF3tCfIf3mvNDEvKI3txhmWyEZHvf4usV/5s4mo9+pGDRE6JwU3elQjmCjsx1R4vZbqKbArT75tN2TDMDnfymFGkb8lMI+m+kLx3qCYYk2HYG1hTYnb0FX84sEuo/W5ZgnfzUb1QNu2b00CMxP2W3i1s= enable_passwordless_sudo: true
57 | Low | stig_rhel9.yml | Applies a STIG hardening role to RHEL 9 hosts, with the role name passed as a variable (var_role). | 0 |  |  |  |  | stig | XL | RHEL 9 STIG role (role name as variable). Same scale as rhel9STIG — hundreds of tasks. Review full role. | 1S_EMAT-RHEL9-STIG | ssh | Dynatrace System | RHEL | SSH Connection | Yes — Role: roles/{{var_role}}/ (role name supplied at runtime via extra vars) | Playbook: stig/stig_rhel9.yml Role: stig/roles/{{var_role}}/ | 1S_EMAT-RHEL9-STIG
58 | Low | show_discovery.yml | Runs 'show cdp neighbor detail' and 'show vpc' on Nexus switches for network discovery. | 0 |  |  |  |  | networking | S | Runs show cdp neighbor detail and show vpc. Read-only — no config changes. Very simple. 3 templates per site. | 1N_NET_HST_Nex9k_discovery 1N_NET_EW_Nex9k_discovery 1N_NET_MDC_Nex9k_discovery | ssh | HST-Nex9k-key, EW-Nex9k, MDC-Nex9k | Cisco NX-OS | SSH Connection | No | Playbook: networking/show_discovery.yml | 1N_NET_HST_Nex9k_discovery extra_vars: _groups: n9kv | 1N_NET_EW_Nex9k_discovery extra_vars: _groups: n9kv | 1N_NET_MDC_Nex9k_discovery extra_vars: _groups: n9kv
59 | Low | stig_vcenter8.yml | Comprehensive vCenter 8.0 STIG hardening playbook applying roles for EAM, Envoy, Lookup, Perfcharts, PostgreSQL, STS, UI, VAMI, and the underlying Photon OS (supports Photon 3, 4, and 5) with granular control toggles per STIG finding. | 0 |  |  |  |  | stig | XL | Massive vCenter 8.0 STIG: 11 roles (EAM, Envoy, Lookup, Perfcharts, PostgreSQL, STS, UI, VAMI, Photon 3/4/5) with per-finding toggles. Connects via SSH to VCSA. Break into sub-workflows per service. | 1S_ConvergedL3_STIG_vCenter 1S_ConvergedL3_STIG_vCenter_Prompted_User | root on the specified vCenter system | vCenters | vCenter (VCSA) | SSH Connection | Yes — Roles: roles/eam/, roles/envoy/, roles/lookup/, roles/perfcharts/, roles/postgresql/, roles/sts/, roles/ui/, roles/vami/, roles/vmware-photon-{3,4,5}.0-stig-ansible-hardening/ | Playbook: stig/stig_vcenter8.yml Role: stig/roles/eam/ Role: stig/roles/envoy/ Role: stig/roles/lookup/ Role: stig/roles/perfcharts/ Role: stig/roles/postgresql/ Role: stig/roles/sts/ Role: stig/roles/ui/ Role: stig/roles/vami/ Role: stig/roles/vmware-photon-{3 | 1S_ConvergedL3_STIG_vCenter | 1S_ConvergedL3_STIG_vCenter_Prompted_User
60 | Low | stig_windows.yml | Applies the Windows Server 2022 STIG hardening role to targeted Windows hosts. | 0 |  |  |  |  | stig | XL | Windows Server 2022 STIG role. Hundreds of registry, policy, and config tasks. Review roles/win2022STIG/ in full. Consider phased conversion by STIG category. | 1S_EMAT_WinRM-Servers-STIG | domain service account | WinRM_servers | Windows | PowerShell Host | Yes — Role: roles/win2022STIG/ | Playbook: stig/stig_windows.yml Role: stig/roles/win2022STIG/ | 1S_EMAT_WinRM-Servers-STIG
61 | Low | vm_port_test.yml | General multi-port connectivity test: iterates over VMs and checks multiple ports via an external tasks file. | 0 |  |  |  |  | admins | S | Port connectivity tests from Ansible host to target VMs. Uses wait_for on multiple ports. External task file. Simple socket-check logic. | 1A_EMAT-Aria-vROPS_Port-Test 1A_EMAT_Port-Test 1A_Port-Test_VxRManagers | ssh | aap controller, Ansible System | Linux (Ansible host) | SSH Connection | Yes — Task file: tasks/ports_check.yml | Playbook: admins/vm_port_test.yml Task: admins/tasks/ports_check.yml | 1A_EMAT-Aria-vROPS_Port-Test extra_vars: var_list_vm: - esocoowvarc01.washdc.state.sbu var_test_port: -1514 -9543 -6514 -8553 -443 | 1A_EMAT_Port-Test extra_vars: var_list_vm: - cvso26zbs001.washdc.state.sbu - cvsoowzbs001.washdc.state.sbu - cvsoewzbs001.washdc.state.sbu - 10.3.130.2 - cvsoewzbp001.washdc.state.sbu var_test_port: - 22 | 1A_Port-Test_VxRManagers
62 | Low | vm_port-test_TCP22.yml | Tests TCP port 22 connectivity from the Ansible host to a list of VMs/hosts with a 1-second timeout. | 0 |  |  |  |  | admins | S | Tests TCP/22 only. Single-port check with 1-second timeout per host. | 1A_EMAT-PFX_Port-Test | ssh (with sudo) | Ansible System | Linux (Ansible host) | SSH Connection | No | Playbook: admins/vm_port-test_TCP22.yml | 1A_EMAT-PFX_Port-Test extra_vars: var_list_vm: - cvso26MVM153.washdc.state.sbu - cvso26MVM154.washdc.state.sbu - cvso26MVM155.washdc.state.sbu - cvso26MVM1.washdc.state.sbu - cvso26MVM2.washdc.state.sbu - cvso26MVM3.washdc.state.sbu - cvso26MVM4.washdc.state.sbu - cvso26MVM5.washdc.state.sbu - cvso26MVM6.washdc.state.sbu - cvso26str014-strg.washdc.state.sbu - cvso26str015-strg.washdc.state.sbu - cvso26str016-strg.washdc.state.sbu - cvso26str024-strg.washdc.state.sbu - cvso26str025-strg.washdc.state.sbu - cvso26str026-strg.washdc.state.sbu - cvso26SVM011.washdc.state.sbu - cvso26SVM012.washdc.state.sbu - cvso26SVM013.washdc.state.sbu - cvso26SVM021.washdc.state.sbu - cvso26SVM022.washdc.state.sbu - cvso26SVM023.washdc.state.sbu - cvso26SVM131.washdc.state.sbu - cvso26SVM132.washdc.state.sbu - cvso26SVM133.washdc.state.sbu - cvsoEWMVM1.washdc.state.sbu - cvsoEWMVM2.washdc.state.sbu - cvsoEWMVM3.washdc.state.sbu - cvsoewstr114-strg.washdc.state.sbu - cvsoewstr115-strg.washdc.state.sbu - cvsoewstr116-strg.washdc.state.sbu - cvsoewstr117-strg.washdc.state.sbu - cvsoEWSVM111.washdc.state.sbu - cvsoEWSVM112.washdc.state.sbu - cvsoEWSVM113.washdc.state.sbu - cvsoOWMVM165.washdc.state.sbu - cvsoOWMVM166.washdc.state.sbu - cvsoOWMVM167.washdc.state.sbu - cvsoOWMVM178.washdc.state.sbu - cvsoOWMVM179.washdc.state.sbu - cvsoOWMVM180.washdc.state.sbu - cvsoOWMVM39.washdc.state.sbu - cvsoOWMVM40.washdc.state.sbu - cvsoOWMVM41.washdc.state.sbu - cvsoOWMVM77.washdc.state.sbu - cvsoOWMVM78.washdc.state.sbu - cvsoOWMVM79.washdc.state.sbu - cvsoowstr016-strg.washdc.state.sbu - cvsoowstr017-strg.washdc.state.sbu - cvsoowstr018-strg.washdc.state.sbu - cvsoowstr054-strg.washdc.state.sbu - cvsoowstr055-strg.washdc.state.sbu - cvsoowstr056-strg.washdc.state.sbu - cvsoOWSVM013.washdc.state.sbu - cvsoOWSVM014.washdc.state.sbu - cvsoOWSVM015.washdc.state.sbu - cvsoOWSVM051.washdc.state.sbu - cvsoOWSVM052.washdc.state.sbu - cvsoOWSVM053.washdc.state.sbu - cvsoOWSVM151.washdc.state.sbu - cvsoOWSVM152.washdc.state.sbu - cvsoOWSVM153.washdc.state.sbu - cvsoOWSVM201.washdc.state.sbu - cvsoOWSVM202.washdc.state.sbu - cvsoOWSVM203.washdc.state.sbu var_test_port: - 22
63 | Low | windows_registry/iPost_resolution.yml | Windows Server security hardening for iPost remediation: disables SSL 2.0/3.0 and TLS 1.0/1.1 while enabling TLS 1.2/1.3 via registry, configures Memory Management speculative-execution mitigations, and enforces NLA for RDP. | 0 |  |  |  |  | psscript | M | Direct registry manipulation — disables old SSL/TLS, enables TLS 1.2/1.3, speculative execution mitigations, NLA enforcement. No external scripts — all inline. Maps directly to PowerShell registry commands. | 1P_EMAT_iPOST_registry_fix | domain service account | Dynatrace Windows ActiveGate | Windows | PowerShell Host | No | Playbook: psscript/windows_registry/iPost_resolution.yml | 1P_EMAT_iPOST_registry_fix
64 | Low | zab_token_renewal.yml | Extends Zabbix user API token expiration. Authenticates to JSON-RPC API, looks up user/tokens, calculates new expiration from days/months/years/never-expire, updates tokens, displays summary, logs out. | 0 |  |  |  |  | dev | M | JSON-RPC API calls to Zabbix. Auth, lookup user/tokens, calculate expiration, update, logout. Map each API call to Orchestrator REST operation. Supports days/months/years/never-expire. | 1D_EMAT_ZabbixToken_Extend | ssh | Ansible System | Zabbix (API) | REST Host | No | Playbook: dev/zab_token_renewal.yml | 1D_EMAT_ZabbixToken_Extend